## WIGS 1112
Naugatuck Valley Community College Operational Plan for Academic Year 2011-2012
IMPLEMENTING OUR WILDLY IMPORTANT GOALS (WIGs)
Strategic Priority
Making sure that we are organized to maximize student success.
The Three Goals
1. | Create an environment in which student success is an expectation.
2. | Balance enrollment demands and services with existing resources while maintaining flexibility to manage and improve efficiency.
3. | Diversify and strengthen resource development and external funding.
The SIX Levers
1. | Redesign and innovation
2. | Integration of academic and student success
3. | Assessment
4. | Data and measurement
5. | Curriculum alignment
6. | Professional development | `
Ten Anticipated Outcomes by 2013 (from NVCC 2010-2013 Strategic Plan)
1. | FTE enrollment will increase by 20%.
2. | Retention rate will increase by 20%.
3. | Graduation rate will increase by 100%.
4. | Certification completion rate will increase by 100%.
5. | Job placement rate for NVCC's graduating class will increase by at least 25% each year.
6. | Grant funding will increase by 25%.
7. | The number of employers visiting NVCC's campus will increase by 25% each year.
8. | The number of community residents retrained for jobs via our programs will increase by 24%.
9. | The transfer rate will increase by 15%.
10. | The average annual income of associate degree earners will increase by at least 25% within a year of graduation.

## Pres.Goals
Presidential Goals for Academic Year 2011-2012:
1 | Successful implementation of the second year of the strategic plan for the College.
2 | Completion of the work by a Task Force and committees and preparation of self-study for NEASC 2012 site visit.
3 | Successful implementation of a new Freshman Year seminar, full development of a developmental summer bridge program and self-paced and other initiatives to support developmental education; establishment of a solid service learning initiative, development and implementation of assessment models that deepen our understanding of the progress we are making or need to make.
4 | Expanded services at the Academic Center of Excellence, and the creation of innovative programs to support students’ successful navigation of developmental courses and our general education offerings.
5 | Aligning the work of Student Services and Academic Affairs to strengthen the continued implementation of a comprehensive Academic Advisement program for the campus.
6 | Creation of a Job Placement Center designed to redeploy staff, consolidate efforts and maximize impact of services in this area.
7 | Successful implementation of an Honors Program.
8 | Full implementation of the proposed plan to expand services in the Danbury area and acquire additional space in an appropriate location.
9 | Continued strengthening of cultural life on campus in particular in our Arts and Humanities area.
10 | Full implementation of the Mentoring program and successful launching of General Education initiative, Year 3.
11 | Continued efforts to expand workforce development programs both on the main campus and at our Danbury site.
12 | Full implementation of cyclical assessment and program reviews for all departments.
13 | Creation and full implementation of an active Alumni Association.
14 | Continue exploration of planning for the construction of a Middle College on campus.
15 | Fund raising to support campus initiatives.

## WIG 1
WIG 1. Create an environment in which student success is an expectation.
| Unit: Department | Initiatives and Activities | WIGs Lever | "10 Anticipated Outcomes" | Presidential Goal | Leader(s) for Implementation | NEASC Standard | Status: Dec. 1 | Status: Mar. 1 | Final Status: May 1
1 | AA | Continuation of work on the NEASC 2012 self-study in preparation for site visit; Task Force and committees will meet regularly throughout the year with open forums held for college community. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment; Professional development. | Anticipated Outcomes 1-10 | Goal 2 | Sandra Palmer Kim O'Donnell Estela Lopez | We will support all Standards. | Work in progress. Description phase completed; Appraisal phase due December 1; NEASC Grab-Bag information session for college community scheduled December 1.
1a | AA: Allied Health | Active participation by division representatives to NEASC committees. Report of committee work at each division meeting. Timely support of NEASC committees' requests for data and information. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum Alignment. | Anticipated outcomes 1-10 | Goal 2 | Interim ADD, Eileen George, and NEASC Committees Representatives: L. Brown M. Manka J. Levesque H. Belcourt S.Anderson J. Pronovost T. Santos C. Lacouture M. Guerrera P. Beaupre | Standards 1-11 | NEASC representatives continue active participation in NEASC Committees (C. Lacouture has resigned from her committee due to PTA program needs.) See division meeting minutes for updates. Data provided to committees as requested.
1b | AA: Arts and Humanities | Reorganize the departments to streamline processes, enable efficiencies, and facilitate the sequencing of courses and the alignment of course objectives to impact retention rates and student success efforts. | 1 and 5 | Anticipated Outcomes 2, 3 | Goals 1, 3 | PamelaTolbert-Bynum and department chairs. | Standard 4 | The reorganization is complete. We have moved from 4 departments to 3, with no additional staff increases. The collaboration of chairs has, to date, allowed us to address course sequencing, the streamlining of processes, and budgetary efficiencies.
1c | AA: Behavioral and Social Sciences | Finalize development and pilot use of "Standard Annual Checkup" Refine advising sheets and advising system to promote communication between students, faculty, and the division office, and to encourage students to take additional responsibility for getting timely advisement. Work with faculty to document, report, and share pedagogical innovations within and across departments/programs. | 1. Redesign and innovation. 2. Integration of academic and student success. 3.Assessment 4. Data and measurement. 5. Curriculum alignment. 6.Professional development. | 1. FTE enrollment will increase by 20%. 2. Retention rate will increase by 20%. 3. Graduation rate will increase by 100%. 4. Certification completion rate will increase by 100%. 9. The transfer rate will increase by 15%. | Goals 1-5 | BSS division director, BSS department chair and program coordinators. | Standards 4, 5, 6, 10, 11 | Partially completed. Standard Annual Checkup (now known as the "Dashboard Report") has been finalized. Advising sheets are finalized, but the division will discuss refinement of the advisement process in spring 2012. Beginning in spring 2012, division meetings will feature "Teaching Conversations" where faculty will raise and issues around teaching in BSS.
1d | AA: Business | Leadership and divisional support in the NEASC process. Provide feedback to NEASC committee, attend and support meetings and focus groups. Communicate NEASC information to the divisions by means of email and at division meetings. Provide data and write ups as appropriate. | 1. Redesign and innovation. 2. Integration of academic and student success. 3.Assessment 4. Data and measurement. 5. Curriculum alignment. 6.Professional development. | Anticipated Outcomes 1, 2, 3, 4, 5, 6, 7, 8, 9, 10 | Goals 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, & 15 | Mitch Holmes Mike Labet chairs standard 9 and Bill Verespy, Elma Solomon, Donna Marotti, Robyn Jay-Bage, and Walter Lippincott are all committee representatives. | Standards 4, 5, 9 | NEASC is through the appraisal stage and on target to meet set deadlines.
1e | AA: STEM | At least two key ET personnel to support NEASC self study through committee and task force involvement. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment. | Anticipated Outcomes1, 2, 3, 4, 9 | Goal 3 | Mia Samsel | Standards 4, 5, 6 | Ren Sharma, Osiris Rosales have been involved in NEASC task force.
2 | AA | Development of Academic Master Plan; kick off will begin June 30, 2011 with directors of the academic unit to begin preparation of plan; work will continue throughout the year to develop a 5-year plan for the unit. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment; Professional development. | Anticipated Outcomes 1-10 | Goals 3, 4, 5, 6, 9, 12 | Sandra Palmer Estela Lopez |  | In progress. Goals have been established and approved and Academic Council is working on goals regarding strategies, leader, resources, academic year, and outcomes.
2a | AA: Allied Health | Academic Master Plan (AMP) shared with the division at August meeting. Faculty were encouraged to provide input to Dean of AA related to AMP. Directors will begin preparation of the 5-year plan. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum Alignment. | Anticipated Outcomes 1-10 | Goals, 1, 12 | Interim ADD | Standards 4, 6 | In progress. Goals have been reviewed with division. E. George participating in writing Goal 4 of Master Plan.
2b | AA: Arts and Humanities | Begin program reviews for appropriate departments and revisit past reviews to determine areas of weaknesses and strengths. This observation will lead to restructuring and streamlining when and where necessary to impact student success. | 1, 3, 5 | Anticipated Outcomes 2, 3, 4 | Goals 1, 3, 12 | PamelaTolbert-Bynum and department chairs. | Standard 4 | We have begun the process of formatting program/discipline review committees. One major challenge is locating an external consultant who can commit to this process.
2c | AA: Behavioral and Social Sciences | 1. Develop common assessments for all BSS introductory courses, to be piloted F12. | 1. Redesign and innovation. 3.Assessment 4. Data and measurement. 5. Curriculum alignment. | 2. Retention rate will increase by 20%. 3. Graduation rate will increase by 100%. 4. Certification completion rate will increase by 100%. 9. The transfer rate will increase by 15%. | Goals 1-5 | BSS division director, BSS department chair and program coordinators. | Standard 4 | In progress. BSS faculty are establishing objectives and measureable learning outcomes for all courses. Once completed and approved, work on common assessments can begin (this process is expected to continue through the spring 2012 semester.)
2d | AA: Business | Introduce and discuss Academic Master Plan at the first Fall Davison meeting. Provide feedback to the academic dean. Division is very involved and has leadership roles in First Year Experience, Honors, and Enrollment Management committee. | Levers 1-6 | Anticipated Outcomes 1-10 | Goals 1-15 | Mitch Holmes, chairs and coordinators. Mitchell Holmes co-chairs FYE Committee; Robyn-Jay Bage chairs Honors committee. | We will support all Standards. | CIS program review completed 11-11-11. Legal Assistant program completed, waiting for a review date. Marketing and fire tech. are still in progress.
2e | AA: STEM | ET Director to support development of Academic Master Plan and four year plan. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment; Professional development. | Anticipated Outcomes 1-10 | Goals 3, 4, 5, 6, 9, 12 | Mia Samsel | Standards 4, 5, 6 | In progress.
3 | AA | Promote curriculum development within the academic units and launch First Year Experience, learning communities, Honors Program, summer bridge programs and self-paced developmental courses and service learning initiative; successfully launch the General Education initiative, year 3. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment; Professional development. | Anticipated Outcomes1, 2, 3, 4, 9 | Goal 3 | Sandra Palmer | Standards 4, 5, 6 | First Year Experience launched fall 2011; Honors Institute will begin spring 2012; bridge programs in developmental math and English are underway, and proving to be successful; General Education initiative, year 3 is moving forward with continuous work being done by the divisions.
3a | AA: Allied Health | Explore division needs related to retention at September division meeting. Schedule one professional development activity based on identified needs for fall and one for spring semester. Continue to develop and implement retention strategies. | Redesign and innovation; Integration of academic and student success; Assessment; Curriculum alignment; Professional development. | Anticipated outcomes 1, 2, 3 | Goal 3 | Interim ADD and program coordinators. | Standards 4, 6 | Division Strategic Plan related to retention reviewed and priorities discussed at August meeting. Presentation to the division on Oct. 24 by Tom Clark concerning "Academic Dismissals and the Student Conduct Policy". Spring activity on the topic of retention being planned.
3b | AA: Arts and Humanities | Continue to focus on the needs of developmental education students via creation of a strategic review committee; innovative programs and redesigned curricula; and assessment efforts that are aligned with collegiate English. | 1, 3, 5 | Anticipated Outcomes 1, 2, 3, 4 | Goal 3 | PamelaTolbert-Bynum and chair for developmental and collegiate English. | Standards 2, 4 | We have begun the process. The chair of Developmental Education is working on the summer's Express Start initiative. Funding is a concern. Department meetings are scheduled regarding assessment efforts AND alignment of obligations/outcomes with collegiate English.
3c | AA: Behavioral and Social Sciences | Conduct curriculum mapping in all degree programs in order to ensure that courses are aligned with institutional (General Education) and programmatic goals/outcomes. | 1. Redesign and innovation. 3.Assessment 4. Data and measurement. 5. Curriculum alignment. | 1. FTE enrollment will increase by 20%. 2. Retention rate will increase by 20%. 3. Graduation rate will increase by 100%. 4. Certification completion rate will increase by 100%. 9. The transfer rate will increase by 15%. | Goals 3,10 | BSS program coordinators and department chairs; BSS division director. | Standard 4 | In progress. Program coordinators have participated in training as part of the General Education/NEASC effort. The curriculum mapping is being done in conjunction with the establishing of objectives/outcomes.
3d | AA: Business | Review Division's Retention plan including advisement, Academic Early and Midterm Warning systems and graduation phone calls and letters. Explain to the academic departments that are joining the division how our plan works and their required involvement. Discuss and implement changes to improve the current plan. Review last year's data and refine steps to insure better retention. Several faculty are teaching FYE. | Levers 1-6 | Anticipated Outcomes, 1, 2, 3, 4, 5, 6, 9 & 10 | Goals 1, 3, 4, 5, 7, 8, 9, 10, & 12 | Division director, chairpersons and coordinators. | Standards 2, 4 | The division is in the process of completing four program reviews. Three are written and one, computer information systems has had their final review. All division faculty are advising and four faculty taught FYE in the fall 2011 semester. Data has been updated and reviewed in each program.
3e | AA: STEM | Promote curriculum development within the academic units as per ABET standard, and encourage faculty involvement in First Year Experience, learning communities, Honors Program. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment; Professional development | Anticipated Outcomes1, 2, 3, 4, 9 | Goal 3 | Mia Samsel | Standards 4, 5, 6 | In progress - Manufacturing certificate is being updated, ABET ET programs are being assessed against CCSU transfer criteria.
4 | AA: | Continuation of cyclical assessment and program reviews in all academic units; 2011-2012 if first year of new program review model and new 5-year cycle | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment. | Anticipated Outcomes 1, 2, 3, 4, 5, 8, 9, 10 | Goal 12 | Sandra Palmer | Standard 4 | Twenty-nine program and discipline reviews are underway this academic year with all programs and discipline reviews now on a 5-year cycle. The new format is being used beginning this academic year.
4a | AA: Allied Health | Continue data collection begun in 2010 and 2011. Report data in September and April Division meetings. Evaluate retention and advising activities. Support PTA Program preparation for accreditation self study. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment; Professional development. | Anticipated outcomes 1, 2, 3, 8, 9, 10 | Goals 2,12 | Interim ADD and program coordinators. | Standard 4 | In progress. Data collection coordinated by T. Santos. Report given at September Division meeting. Evaluation of retention and advising activities is ongoing. E. George meeting regularly with PTA faculty concerning self study report. C. Lacouture attended self study preparation conference in October. Renovation of PTA lab/classroom space is in progress.
4b | AA: Arts and Humanities | 1. Support NEASC and General Education efforts by providing data when required and ensuring the continuation of assessment efforts in ENG 101 and 102. 2. Focus on assessment efforts for modern languages, communications, philosophy, and the Arts. | 3 and 4 | Anticipated Outcomes1, 2, and 3 | Goals 2, 3, 10 | PamelaTolbert-Bynum department chairs, and faculty. | Standards 4, 11 | Assessment efforts in ENG H101 and H102 are ongoing. Program reviews for the arts and philosophy are on schedule to be completed spring 2012 and will inform our assessment efforts.
4c | AA: Behavioral and Social Sciences | 1. Complete program reviews for behavioral science & DARC. 2. Complete discipline reviews for history, psychology, political science. 3. Complete NAEYC accreditation process for ECE. | 1. Redesign and innovation 2. Integration of academic and student success. 3.Assessment 4. Data and measurement. 5. Curriculum alignment 6.Professional development. | 1. FTE enrollment will increase by 20%. 2. Retention rate will increase by 20%. 3. Graduation rate will increase by 100%. 4. Certification completion rate will increase by 100%. 5. Job placement rate for NVCC's graduating class will increase by at least 25% each year. 9. The transfer rate will increase by 15%. 10. The average annual income of associate degree earners will increase by at least 25% within a year of graduation. | Goal 12 | BSS program coordinators and department chairs; BSS division director. | Standard 4, 6, 11 | Partially complete. 1. Behavioral science program review has been submitted and is being revised. DARC program review is being written. 2. Psychology discipline review has been submitted and is being reviewed by the division director. History and political science are at the early stages. 3. ECE has had its accreditation visit, and is awaiting final word about accreditation status (anticipated January 2012)
4d | AA: Business | Work to insure that all program reviews are current. Carefully review data provided by Institutional Research and the Retention office. Discuss and evaluate chairs and coordinators in their role in curriculum development, evaluation, data collection and retention. | 1. Redesign and innovation 2. Integration of academic and student success. 3.Assessment 4. Data and measurement. 5. Curriculum alignment 6.Professional development. | 1. Redesign and innovation 2. Integration of academic and student success. 3.Assessment 4. Data and measurement. 5. Curriculum alignment 6.Professional development. 7. Employers visiting NVCC will increase 8. Community residents trained for jobs. 9. Transfer rate will increase 10. Annual income for AS Degree will increase. | Goals 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12 | Division director, program chairs, and coordinators. | Standards 4, 5, 9 | Completed. Master plan accepted by division.
4e | AA: STEM | Perform program review in Fire Administration and continue assessment of all ET departments. | Redesign and innovation; Integration of academic and student success; Assessment; Data and measurement; Curriculum alignment. | Anticipated Outcomes 1, 2, 3, 4, 5, 8, 9, 10 | Goal 12 | Mia Samsel | Standard 4 | Fire technology has moved to business division. Physics discipline review has been performed, Developmental math and environmental science program reviews are underway.
5 | AA | Begin to implement the possibility of a high school to college bridge program at the college. | Redesign and innovation; Integration of academic and student success; Curriculum alignment; Data and measurement. | Anticipated Outcomes 1, 2, 3, 4, 9, 10 | Goal 14 | Sandra Palmer Estela Lopez | Standards 4, 6 | The College Access Challenge Grant has opened the possibility to get high school students college ready in their junior year. The initiative begins spring 2012.
5a | AA: Arts and Humanities | Ensure quality and consistency of syllabi; ensure part-time faculty are evaluated, mentored, and aware of responsibilities (office hours); ensure all faculty are aware and take advantage of professional development opportunities, including grant writing and proposal reviews. | 1, 6 | Anticipated Outcomes 2, 6 | Goals 1, 2, 15 | PamelaTolbert-Bynum department chairs, and faculty. | Standard 5 | Syllabi are reviewed each semester and adjunct faculty are made aware of their responsibilities via written and oral venues. Professional development opportunities are announced at division meetings.
5b | AA: Behavioral and Social Sciences | Expand higher education opportunities in the division via development and appropriate expansion of articulation agreements with high schools and other higher education institutions. | 1. Redesign and innovation 2. Integration of academic and student success. | 3. Graduation rate will increase by 100%. 4. Certification completion rate will increase by 100%. 9. The transfer rate will increase by 15%. | Goal 1 | BSS program coordinators, and department chairs; BSS division director. | Standard 4,5,6 | In progress. BSS faculty are currently engaged in higher priority activities more directly related to the upcoming NEASC visit and discipline/program development. This activity will likely be shifted (as a priority) to next academic year.
5c | AA: Business | Participate in the College Bridge Program discussion. If the initiative moves forward, assist with recruitment and support of the program. | 1. Redesign and innovation 2. Integration of academic and student success. 3.Assessment | Anticipated Outcomes 1, 2, 3, 4, 9 & 10 | Goals 1, 5, 9 and possible 14 | Mitchell Holmes | Standard 2, 5 | No activity to report
5d | AA: STEM | Continue growth of College Connections Program. Establish articulation agreement with at least one area high school with an Intro. to Engineering credit course. | Redesign and innovation; Integration of academic and student success; Curriculum alignment; Data and measurement. | Anticipated Outcomes 1, 2, 3, 4, 9, 10 | Goal 14 | Mia Samsel | Standards 4, 6 | In progress. Working with Janice Petrillo to staff Bridge to College program.
6 | AA: Distance Learning | Coordinate and manage institutional deployment of comprehensive training and curriculum development program for online academic initiatives, including curricular review component. | 1 - 6 | Anticipated Outcomes 1, 2, 3, 4, 5, 9 | Goals 1, 3, 4, 10, 12 | Stacey Williams Lewis Boyce | Standards 1, 4, 5, 7, 8 | With transition to Blackboard Learn, all faculty are being trained; online courses are undergoing curricular review.
7 | AA: Distance Learning | Begin process of revising existing Blackboard Vista training materials and curriculum to aligning with Blackboard Learn. Develop new curriculum and materials as necessary. | 1 - 6 | Anticipated Outcomes 1, 2, 3, 4, 5, 9 | Goals 1, 3, 4, 10 | Stacey Williams Lewis Boyce | Standards 1, 4, 5, 7, 8 | In Progress.
8 | AA: Distance Learning | Coordinate and manage local roll-out 1 and 2 of Blackboard Learn 9.x in anticipation of system deployment fall 2012; use the transition as an opportunity to promote and support the effective use of technology in meeting educational goals, and foster an environment in which educational technology is used to provide the best possible educational experience for our students. | 1 - 6 | Anticipated Outcomes 1, 2, 3, 4, 5 | Goals 1, 3, 4, 10 | Stacey Williams Lewis Boyce | Standards 1, 4, 5, 7, 8 | 37 NVCC faculty (FT and PT) have been trained, 11 of whom are/will be teaching live courses in Learn. In fall 2011, 7 courses (online and traditional) are utilizing Blackboard Learn; in spring 2012, 21-26 courses will utilize Blackboard Learn.
9 | AA: IR | Support assessment of student based outcomes through systematic collection/generation of data which can be aligned with objective standards for measuring student success. | 1,3,4 | Anticipated Outcomes 2, 3, 4, 6 | Goals 1, 2, 3, 12 | Sandra Palmer Lauren Friedman | Standards 4 ,6 , 11 | Various tools for measuring student based outcomes have been developed by IR in collaboration with the Dean for Academic Affairs, including: surveys, program and course based enrollment/completions data, comparative studies related to distance and on-ground learning. An evaluation of IDS/FYE is in process.
10 | AA: ACE | Expansion of student tutoring program to help students directly and positively interact with peers while providing assistance. | 1, 2 | Anticipated Outcomes 1, 2, 3 | Goal 4 | Kathy Taylor | Standard 6 | Working closely with the Federal Work Study Coordinator, the ACE employs seven work study students and fourteen student assistants.
11 | AA: ACE | Continued tutor training development and implementation of on-line module delivery. | 1, 2 | Anticipated Outcomes 1, 2, 3 | Goal 4 | Kathy Taylor | Standards 2, 6 | Ongoing tutor training workshops are conducted throughout the semester. The development of a two-day tutor training orientation beginning January 2012 is underway.
12 | AA: ACE | Collaborate with math faculty to pilot MyMath Test in two courses to determine impact of refresher software on student performance. | 1, 2 | Anticipated Outcomes 1, 2, 3 | Goal 4 | Kathy Taylor | Standards 4, 6 | Math faculty and testing coordinator refer individual students to ACE to receive MyMath Test software to refresh. Stalled progress taking pilot from individual level to course wide.
13 | AA: ACE | Active marketing campaign to attract students enrolled in developmental courses to Academic Center. | 1, 2 | Anticipated Outcomes 1, 2, 3 | Goal 4 | Kathy Taylor | Standards 6, 10 | All students enrolled in developmental math courses receive monthly email blasts promoting the ACE. In early talks with math faculty to implement pilot referral system for all developmental students in spring 2012. Referral form developed by math faculty.
14 | AA: ACE | Create and implement faculty evaluation procedure where student and professional tutors are evaluated for content knowledge. | 1, 2 | Anticipated Outcomes 1, 2, 3 | Goal 4 | Kathy Taylor | Standards 4, 5 ,6 | Math faculty continue to conduct individual tutor evaluations. Procedure implemented across accounting and writing as well. Continued outreach to science faculty to recruit evaluator.
15 | AA: ACE | Continue data collection and assessment to determine most effective ways to assist students. | 1, 2 | Anticipated Outcomes 1, 2, 3 | Goal 4 | Kathy Taylor | Standards 2, 6 | Ongoing troubleshooting with IR and IT surrounding Tutortrac's data collection. Planned Tunxis visit with IR to determine how to better use the available software.
16 | AA: Library | Expand student services/access by increasing the hours that the library is open to the public. | 1, 2 | Anticipated Outcomes 1, 2, 3, 4, 6, 9 | Goal 4 | Samuel Brown | Standards 6, 7 | The library has added Sunday hours (10am-2pm) at no expense to the college.
17 | AA: Library | Library will pilot clicker technology in the Freshman Year seminar that assists outcomes assessment of library instruction by providing pre-test and post-test feedback. | 3, 4 | Anticipated Outcomes 2, 3, 4, 6, 9 | Goal 3 | Samuel Brown | Standards 4, 7 | Planning is ongoing. Implementation will occur during spring 2012.
18 | AA: Library | Library will increase by 5% over AY1011 its instruction on information literacy, website evaluation, plagiarism, and database search techniques. | 2 | Anticipated Outcomes 1, 2, 3, 4, 6, 9 | Goal 4 | Samuel Brown | Standard 7 | Ongoing. Statistics from fall 2011 are in the process of being collected.
19 | AA: Bridge to College | Strengthen Bridge to College initiative by implementing grants. | 2,5 | Anticipated Outcomes 1, 2 | Goal 14 | Janice Petrillo John Corcoran Estela Lopez | Standard 6 | All grants are in progress. Facilities are being renovated.
20 | AA: Bridge to College | Seek additional grant opportunities to strengthen relationships between high school and college. | 1 | Anticipated Outcome 6 | Goal 15 | Janice Petrillo John Corcoran Estela Lopez | Standard 6 | Additional resources were obtained to support the expansion of the College Access Grant Program.
21 | AA: Women's Center | Continue to develop an action plan to connect the center's activities to the college. | 2 | Anticipated Outcome 1 | Goal 9 | Estela Lopez Yhara Zelinka | Standard 6 | Submitted grant to Connecticut Community Foundation. Met with advisory group.
22 | AA | Complete area websites within Academic unit. | Redesign and innovation. | Anticipated Outcomes 1, 2, 3, 4, 5 | Goal 2, 5 | Area directors | Standards 4, 8, 10 | In progress; divisions are working on content to include in websites.
23 | SS: Dean's Office - Enrollment Mgmt Taskforce | Establish an Enrollment Management Committee with sub-committees in the areas of recruitment, retention and graduation set benchmarks that align with the strategic plan. | 1, 2, 3 | Anticipated Outcomes 2, 3 | Goal 1 | L. Ortiz S. Palmer L. Stango B. Mattheis K. Taylor C. Hardy M. Holmes T. Violante L. Friedman J. Arbusto | Standards 5, 6, 8, 9 | EMC has been meeting for the past semester and making steady progress.
24 | SS: Dean's Office -Enrollment Mgmt - Recruitment sub committee | Recruitment sub-committee to create an expanded recruitment plan as part of enrollment management. | 1, 2, 3 | Anticipated Outcomes 2, 3 | Goal 1 | Lillian Ortiz Linda Stango and admissions staff. | Standards 5, 6, 8, 9 | First draft of the recruitment plan has been reviewed with the EMC. They will start to revisit it again and be prepared to vet it with various college governance groups like Academic Council, Cabinet, Faculty Senate, etc.
25 | SS: Dean's Office -Enrollment Mgmt - Retention sub committee | Review present retention and work on a plan that will track, support and guide the initiatives that are planned for the institution around retention efforts. | 1, 2, 3 | Anticipated Outcomes 2, 3 | Goal 1 | Lillian Ortiz Bernd Mattheis | Standards 5, 6, 8, 9 | Nine elements of the Draft Retention Plan have been refined and progress is being tracked in each area.
26 | SS: Dean's Office -Enrollment Mgmt - Graduation sub committee | Review present graduation benchmarks in the strategic plan and determine what new or on-going initiatives are relevant to increasing graduation and transfer. | 1 ,2, 3 | Anticipated Outcome 3 | Goal 1 | L. Ortiz S. Palmer J. Arbusto L. Friedman | Standards 5, 6, 8, 9 | First draft of the graduation plan has been reviewed with the EMC. They will start to revisit it again and be prepared to vet it with various college governance groups like Academic Council, Cabinet, Faculty Senate, etc. Graduation sub-committee has worked with OIR to get data to be included in Enrollment Management Plan.
27 | SS: Dean's Office | Update the Student Handbook and ensure that it is widely disseminated. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | L. Ortiz D. Zutant T. Violante A. Egan | Standards 5, 6, 8, 9 | Student handbook has been updated with new advisors list, Board of Regents information and new hires on campus. Further, a table of contents was added. The handbook is comprehensive but reorganization of the document needs to be considered.
28 | SS: Dean's Office | Each department will be asked to assign a point person for the web who will be responsible for content and updates monthly. Dean will report the names to the NEASC Public Disclosure committee to ensure compliance. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | L. Ortiz L. Stango C. Hardy B. Mattheis K. Blake | Standards 5, 6, 8, 9 | Each department has assigned a point person. Three meetings have been held with staff to identify broken links, update content, contacts, and add pages.
29 | SS: Admissions/ CAPSS | A dual database will be developed in coordination with IT that will facilitate an appointment being made for testing and advising simultaneously. | 1 | Anticipated Outcome 1 | Goal 1 | B. Mattheis L. Stango C. Cyr C. Larkin | Standards 5, 6, 8, 9 | Due to lack of staff in IT that has the ability to program this functionality we are on a holding pattern. (New Student Success Sessions are already scheduled for spring '12 term; fall '12 term dates to be determined before end of Jan. 12).
30 | SS: CAPSS/ Testing | A database will be developed to allow for students to make their testing appointments on-line. | 1 | Anticipated Outcome 1 | Goal 1 | B. Mattheis C. Cyr C. Larkin | Standards 5, 6, 8, 9 | Due to lack of staff in IT that has the ability to program this functionality we are on a holding pattern.
31 | SS: CAPSS/ Testing | Implement new testing requirements for ACT scores - BOT policy 3.19. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | C. Cyr B. Mattheis S. Vaichus | Standards 5, 6, 8, 9 | Complete.
32 | SS: Financial Aid Office | Promote College Goal Sunday as an annual event at Naugatuck Valley Community College so that applying for college does not become an obstacle that would keep them from pursuing an education beyond high school. | 1, 2, 3 | Anticipated Outcomes 2 ,3 | Goal 1 | Cathy Hardy and financial aid staff. | Standards 5, 6, 8, 9 | In the planning stages. Will be implemented in the spring. Many evening financial aid workshops have taken place this fall.
33 | SS: Financial Aid Office | Disseminating Financial Aid information to students via book marks, letters, emails and posters in an effort to raise awareness of financial aid literacy. | 1, 2, 3 | Anticipated Outcomes 2 ,3 | Goal 1 | Cathy Hardy and financial aid staff. | Standards 5, 6, 8, 9 | On-going, but the implementation of the activities has taken place.
34 | SS:Student Activities | Student Activities/SGA Events Calendar - Work with Web Services and SGA Clubs to promote and improve Student Activities Event Calendar. Increase student participation in events by posting all student events at one convenient location on the website under student life for students to search. | 1, 2, 3 | Anticipated Outcomes 2 | Goal 1 | Karen Blake Daniel Wallace | Standards 5, 6, 8, 9 | New activities such as the Country Fair had excellent attendance. Expansion of the web calendar is on-going.
35 | SS:Student Activities | Improve New Student Orientation event on campus. Promote participation from all departments on campus. | 1, 2, 3 | Anticipated Outcomes 2, 3 | Goal 1 | K. Blake L. Ortiz L. Stango H. Carrasquillo | Standards 5, 6, 8, 9 | Implemented the New Student Orientation. Successful with 550 students and parents in attendance.
36 | SS:Student Activities | Work w/SGA/Clubs to plan a fall event called "Fall Country Fair" for student participation similar to "Spring Fling." | 1, 2, 3 | Anticipated Outcomes 2, 3 | Goal 1 | Karen Blake and SGA Officers | Standards 5, 6, 8, 9 | Complete and successful. Planning to hold it annually if the SGA agrees to fund and support it.
37 | SS:Student Activities | Work w/SGA/Clubs to select a community project within our service region to volunteer and raise funds for their cause. | 1, 2, 3 | Anticipated Outcome 6 | Goal 1 | Karen Blake and SGA Officers | Standards 5, 6, 8, 9 | In progress, working with St. Vincent DePaul, food drive and raising funds to fill the pantry for the winter. Will select a new project for the spring semester.
38 | ADM: Dean | Using a committee of college employees and students, establish an effort entitled the Male Retention initiative to find ways to improve the retention of males at NVCC. | 1, 2, 4 | 2, 3, 4, 9 | NA | James Troup, assisted by Estela Lopez | Standard 6 | First meeting of the semester was held on 10/17/11 with students in attendance. Next meeting scheduled for 12/1/11. Bridge to College staff assisting. Breakfast for male retention initiative was held.
39 | ADM: Dean | Establish a new Job Placement Center by consolidating parts of existing college departments into a new center in order to support and carry out for students the functions of career education and advisement, job placement, job/interview preparation, job fairs, coop placement, work study and student assistant placement on campus, and collaboration with the WIB. | 1 ,2, 4 | 5, 7 | Goal 6 | James Troup, with Mary Ann Fontaine | Standard 6 | Center is furnished and opened. Activities being held. Measurable outcomes proposed to Inst Effectiveness subcomm. of IPC. See items under JPC for more detail.
40 | ADM: CED | Provide a minimum of 2 professional development opportunities for NCLs to include assessment for non-credit courses and classroom management issues. | 2, 3, 6 | Anticipated Outcome 8 | Goal 11 | Laurie Hornbecker Lisa Crick Judy Ouellette | Standard 5 | The first is scheduled for January 18, 2012.
41 | ADM: CED | Explore opportunities to celebrate non-credit student successes. | 1, 2, 3 | Anticipated Outcome 8 | Goal 10 | Laurie Hornbecker PatriciaTargett Sandra Lee | Standard 6 | No progress at this time. Brainstorming session will be held at the professional development session in January.
42 | ADM: Danbury | Establish a dedicated space for a tutoring center on the 3rd floor at 183 Main Street to provide tutoring in writing and mathematics. | Integration of academic and student success. | Retention rate will increase by 20% | full implementation of the proposed plan to expand services in the Danbury area and acquire space in an appropriate location. | Matthew Longcore Kathy Taylor | Standards 6, 8 | Tutoring center in Danbury operated in partnership with the Academic Center for Excellence (ACE), now offers free tutoring in math, writing assistance, and ESL. Tutoring is available Monday through Thursday at specific times.
43 | ADM: Danbury | Establish a new inclement weather/closing policy. | Integration of academic and student success. | Retention rate will increase by 20% | full implementation of the proposed plan to expand services in the Danbury area and acquire space in an appropriate location. | Matthew Longcore | Standards 6, 10 | Inclement weather policy has been recommended whereby the NVCC Danbury Center will comply with the Waterbury campus policy. Exceptions will be made in the event of extreme weather only in the Danbury area.
44 | ADM: Facilities | Electronic message sign at west entrance. | 1 | Anticipated Outcome 2 | N/A | Robert Divjak | Standard 8 | No progress.
45 | ADM: Facilities | Create a committee to review campus obstacles for disabled students. | 1 | Anticipated Outcome 2 | N/A | Robert Divjak | 6, 8 | Need to recruit volunteers from faculty, staff, and students. Possibly a campus-wide email or contact SGA early next semester
46 | ADM: Facilities | Install back-up chilled water pump in Ekstrom Hall. | 1 | Anticipated Outcome 2 | N/A | Robert Divjak | Standard 8 | Requested proposal from HVAC contractor. No response yet. Will call again. March/April time frame for installation work.
47 | ADM: Finance | Implementation of Web based installment plans. | 1 | Anticipated Outcomes 1, 2, 3, 4, 9 | Goal 1 | Lisa Palen System Office DOF Council | Standard 6 | 11/18/11 Joint DOA / DOF meeting agenda Item requesting DOA approval.
48 | ADM: IT | Public Information Kiosks. | 1 | N/A | Goal 1 | Nephtali Villanueva | Standards 6, 7, 8, 10 | New kiosks researched. Learning the software to run the kiosks.
49 | ADM: IT | Ground IT Network spaces. | 1 | N/A | Goal 1 | Bruce Arsenault | Standards 7, 8 | Phase completed by Mercury and inspected by Elert. A very short punch list from Elert has been sent. Mercury will finish the punch list over the semester break
50 | ADM: IT | AC/Venting in IT network spaces. | 1 | N/A | Goal 1 | Nephtali Vilanueva Nicholas Schweitzer | Standards 7, 8 | Requesting quotes from vendors
51 | ADM: IT | Expand Danbury network to 3rd floor. | 1 | N/A | Goal 1 | Bruce Arsenault Conal Larkin | Standards 7, 8 | Completed
52 | ADM: IT | Move the Danbury computer lab to a larger room. | 1 | N/A | Goal 1 | Bruce Arsenault Conal Larkin | Standards 7, 8 | Completed
53 | ADM: IT | Purchase and deploy significant equipment via bonding funds. | 1 | N/A | Goal 1 | Nephtali Vilanueva Conal Larkin | Standards 7, 8 | Computers have been purchased and 75% deployed
54 | ADM: WEB | Create a quarterly newsletter. | 1, 2, 5 | N/A | Goals 1, 4, 5, 12 | Daniel Wallace | Standards 7, 10 | Module purchased; implementation delayed until Spring 2012
55 | ADM: WEB | Create a FAQ about Web Services offerings, policy and procedures. | 1, 2, 5 | N/A | Goals 1, 4, 5, 12 | Daniel Wallace | Standards 7, 10 | Site is ready for release in December
56 | ADM: WEB | Enhance college community's understanding of content: creating, adding, and modifying. | 1, 2, 5 | N/A | Goals 1, 4, 5,12 | Daniel Wallace | Standards 7, 10 | Planning content workshop for 12/9/11
57 | ADM: JPC | Open and offer comprehensive career support and job placement center. | 1, 2, 3, 4, 6 | Anticipated Outcomes 5, 7, 8, 10 | Goals 6, 11 | Jim Troup Mary Ann Fontaine | Standard 6 | Moved into offices the week of 10/11/11. Supporting BSS Co-op and Field Work, Workforce Investment Board clients, career counseling, job postings, and assistance with job searches, resumes, cover letters and interview skills. Currently working on student worker/student assistant process.
58 | ADM: JPC | Promote the use of JPC services to credit and non-credit students. | 2 | Anticipated Outcome 5 | Goal 6 | Mary Ann Fontaine Laurie Hornbecker needs AA rep | Standard 6 | We have begun to visit student clubs and have presented to the Student Government Association. We promote events on the TV screens, flyers and emails to divisions. A customized resume/interview skill/cover letter workshop will be presented to the Accounting Club on 12/1.
59 | ADM: Public Safety | Design and take bids on an IP security camera system for the campus. Award bid if funds available. To include replacement of existing system plus additional cameras. | 1 | Anticipated Outcomes 2, 3, 4 | Goal 1 | Toni Rinaldi Conal Larkin | Standard 8 | Done - completed. January, 2011. Revised proposal with updated prices received 09/11. Waiting release of funds for purchase.
60 | ADM: Public Safety | Encourage all campus personnel not already identified as key campus personnel to participate in the online FEMA training courses. | 2 | Anticipated Outcomes 2, 3, 4 | Goal 1 | Toni Rinaldi | Standard 6 | Done - campus wide email sent 08/31/11.
61 | ADM: Public Safety | Continue training of critical incident management team (CIMT) to include specific roles and responsibilities in ICS. | 2 | Anticipated Outcomes 2, 3, 4 | Goal 1 | Toni Rinaldi | Standard 6 | Ongoing - monthly.
62 | ADM: Public Safety | Expand critical incident management training to include voluntary, campus wide participation. | 2 | Anticipated Outcomes 2, 3, 4 | Goal 1 | Toni Rinaldi | Standard 6 | Initial stage campus wide training in FEMA courses emailed 08/31/11.
63 | ADM: Public Safety | Ensure that critical information related to campus public safety services and procedures is presented to new faculty and students. | 2 | Anticipated Outcomes 2, 3, 4 | Goal 8 | T. Rinaldi S. Palmer J. Troup | Standard 5 | Attending New Student Orientation 01/10/12.
64 | ADM: Public Safety | Plan, organize, implement and evaluate a building evacuation program to support the existing emergency operations plan. | 1 | Anticipated Outcomes 2, 3, 4 | Goal 1 | Toni Rinaldi | Standard 2 | Currently in implementation phase - training in equipment use of IT & Facilities on 11/18/11. PSD trained.
65 | ADM: Public Safety | Plan and hold information sessions to review campus emergency procedures. | 6 | Anticipated Outcomes 2, 3 | Goal 1 | Toni Rinaldi | Standards 2, 5 | Pending BEP (now called BEAR - Building Evacuation and Response) implementation; target implementation date - January, 2012.
66 | HR | Create a program to publicly recognize and reward exemplary service to students by faculty and staff. | 1 | Anticipated Outcomes 2, 3, 4, 5 | Goals 3, 4, 5, 6, 8, 10,11 | A.J. Dubois | Standards 3, 6 | HR is in discussions with Academic Affairs and Student Services to develop a process for nominations and approvals.
67 | HR | Recruit volunteers in support of mentoring, academic advising, job placement and tutoring. | 1 | Anticipated Outcomes 2, 3, 4, 5 | Goals 4, 5, 6, 10 | A.J. Dubois | Standards 3, 6 | On-going. Candidates have been referred.
68 | HR | Coordinate Title IX compliance and expand services to students. | 1 | Anticipated Outcomes 2, 3, 4, 5 | Goals 1, 4 | Jacqueline Swanson Lillian Ortiz | Standards 3, 10 | On-going. Dean Ortiz to attend training in December 2011.
Note on C72: Bob D: There is only one CHW pump presently. There will be no cooling in Ekstrom should this pump fail.

## WIG 2
WIG 2. Balance enrollment demands and services with existing resources while maintaining flexibility to manage and improve efficiency.
| Unit: Department | Initiatives and Activities | WIGs Lever | "10 Anticipated Outcomes" | Presidential Goal | Leader(s) for Implementation | NEASC Standard | Status: Dec. 1 | Status: Mar. 1 | Final Status: May 1
1 | AA | Work closely with Student Services to enhance the college experience for students: academic advisement, one-stop shop registration, new student orientation, job placement center, and ACE. | Integration of academic and student success | Anticipated Outcomes 1, 2, 3, 4, 9, 10 | Goal 5 | Sandra Palmer Lillian Ortiz | Standards 4, 5, 6 | Academic Affairs and Student Services are working well together; monthly meetings, enrollment management committee, academic council, curricular initiatives involve both units.
2 | AA | Continue data collection begun in 2010-2011 related to pre-program advising. Continue advising of all programmatic students. Work with admissions (follow-up to May 2010 meeting with L. Stango, N. Cerruto and I. McGowan) to assist in scheduling and holding information sessions related to division programs. | Redesign and innovation, Integration of academic and student success, and Assessment | Anticipated Outcomes 1, 2, 3, 4 | Goals 3, 5, 6 | Interim ADD and program coordinators. | Standard 5 | On-going.
3 | AA: Distance Learning | Assess and refine Office of Distance Learning communications plan. | 1 - 4 | Anticipated Outcomes 1, 2, 3, 4, 5 | Goals 1, 3, 4, 10, 12 | Stacey Williams Lewis Boyce | Standards 7, 8, 10 | In progress; Dir. of DL met with Dean of Academic Affairs regarding content and direction. Google analytics information pertaining to DL webpage traffic and effectiveness has been collected.
4 | AA: IR | Partner with academic and administrative units to Identify and produce actionable data for planning and assessment. | 2 ,3, 4 | Anticipated Outcomes 1, 2 ,3, 4, 9 | Goals 1, 2, 3, 4 , 5, 6, 7, 8, 11, 12, 15 | Lauren Friedman | Standards 2, 4, 6, 7, 8, 10 | IR provides on-going, direct support in developing the Institutional Effectiveness Plan. IR is actively involved identifying, producing, and communicating actionable multi-year data for use in 1) developing the institution's Enrollment Plan, notably for related sub-committees on Recruitment, Retention, and Graduation and, 2) in support of assessment for all academic programs as well as Distance Learning, First Year Experience and the Academic Center for Excellence and, 3) for planning, assessment, and program development in other units including the Advising Center, Danbury Center and Job Placement Center. IR plays a leadership role in the on-going collaboration with the NEASC Task Force and the standards sub-committees.
5 | AA: IR | Enhance and expand the use of data for decision making through information sessions and presentations that explore the data, data tools, and methods for analysis. | 4, 6 | Anticipated Outcomes 1, 2, 3, 4, 9 | Goals 1, 2, 12 | Lauren Friedman | Standards 2 , 5, 6, 10, 11 | Numerous presentations (Institutional Planning Committee, Academic and Administrative Councils, Student Services) have been given and information sessions (all Academic Divisions, NEASC sub-committees, First Year Experience, Americorps, Male Retention Initiative, Job Placement Center) have been conducted in support of data-based decision making.
6 | AA: IR | Establish routine and timely communication of available data to internal stakeholders using formats that support planning for institutional effectiveness. | 1, 2, 4 | Anticipated Outcomes 1, 2, 3, 4, 9 | Goals 2 ,5, 12 15 | Lauren Friedman | Standards 2 ,5, 6, 10,11 | A schedule providing enrollment, graduation, and transfer data has been developed and adhered to in support of Academic Program Reviews. Student and graduate contact information has been produced and distributed for each academic program including general education. Survey questions and data from prior surveys has been provided to academic programs, NEASC committees, and the Job Placement Center. Data Dashboards have been developed and distributed to the Academic divisions. SharePoint documents have been posted for NEASC. Updates providing information on current enrollments have been made to the IR website.
7 | SS:Dean's Office | Establish a committee composed of Academic and Student Affair professionals to work on establishing an annual Open House - Fall, 20122. | 1, 2, 3 | Anticipated Outcomes 2, 3 | Goal 1 | Lillian Ortiz Linda Stango and division chairs. | Standards 5, 6 | Began to put together the Enrollment Mgt recruitment plan. To date discovered that the divisions don't have any marketing materials to promote their programs which is lynch pin to an Open House.
8 | SS: Dean's Office | Establish a tracking mechanism for student complaints in an effort to target areas for improvement of processes, communications, staff training. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | Lillian Ortiz Diane Zutant and student affairs directors. | Standards 5, 6 | Implemented collecting complaints on forms. Effective because it pinpoints the exact area, person, lack of response the staff is providing. Helps me to secure quicker answers.
9 | SS: Dean's Office | Review and update the Student Affairs web-pages to meet standards. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | Lillian Ortiz Daniel Wallace | Standards 5, 6 | In-process for the NEASC visit. Office of the Dean write up is complete will be trained on how to post on 11/28.
10 | SS: Dean's Office - Retention | Assist with the CT Scholars grant around the male retention initiative. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | Bernard Mattheis Lillian Ortiz Estela Lopez | Standards 5, 6 | Initial activities are being planned.
11 | SS: Admissions | Collaborate and partner with division directors on recruiting events especially on low-enrolled programs. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | L. Stango T. Brown M. Holmes M. Samsel and program coordinators. | Standards 5, 6 | Published invitation to participate in recruiting in the weekly bulletin. Purchased additional materials to support more recruiters and developed a process for coordinating activities.
12 | SS: Admissions | Build and implement a plan to physically re-organize the Admissions Office. | 1,2,3 | Anticipated Outcome 1 | Goal 1 | L. Ortiz L. Stango B. Divjak L. Luciano | Standards 5, 6 | Plan for the Admissions Office was submitted and received funding. We are currently completing phase 1. Phase 2 and 3 are scheduled to begin after the spring enrollment period.
13 | SS: Admissions | Reach out through an E-newsletter to high school counselors and principals. | 1,2,3 | Anticipated Outcome 1 | Goal 1 | Linda Stango and admissions staff. | Standards 5, 6 | Spring 2011 enewsletter was sent out to high school counselors. Fall enewsletter is slated for distribution in early Dec.
14 | SS: Admissions | Build an outreach plan to local middle schools that will complement the high school plan. | 1,2,3 | Anticipated Outcome 1 | Goal 1 | Linda Stango and admissions staff. | Standards 5, 6 | Pending.
15 | SS: CAPSS | Continue to provide coordination to the new advising model with faculty in an effort to support retention to graduation. | 1, 2, 3 | Anticipated Outcomes 1, 2 | Goal 1 | Bernd Mattheis | Standards 5, 6 | Faculty involved as Advisors increased to 125 (including 21 FYE Instructors). Limited advising support added for Danbury Center.
16 | SS: CAPSS - Retention | Build stronger alliance between the CAPSS, ACE and faculty by using an early warning system throughout the year. | 1, 2, 3 | Anticipated Outcomes 2, 3 | Goal 1 | H. Carrasquillo B.Mattheis C. Johnson S. Gager | Standards 5, 6 | Tested Early Earning Format during summer 2011. Revised in conjunction with FYE Coordinators fall 2011. Intend to expand to ENG 43,53,63 & MAT 73.75.95 sections during spring 2012.
17 | SS:Financial Aid Office | Continue to provide financial aid workshops in an effort to award financial aid early so students can register early. | 1, 2, 3 | Anticipated Outcome 2 | Goal 1 | Cathy Hardy and financial aid staff. | Standards 5, 6 | The outcome is continuous and we already have scheduled our workshops for the semester.
18 | SS:Student Activities | Work on streamlining process of Graduation and Student Leadership Banquet within Student Activities Department to build efficiencies. | 1, 2, 3 | Anticipated Outcome 3 | Goal 1 | Karen Blake Alberta Thompson | Standards 5, 6 | Graduation- In progress, waiting on work order submitted to IT to create database to streamline process of ticket distribution. Leadership Banquet- Modified ticket purchase and distribution process for leadership banquet.
19 | ADM: CED | Implement proposed reorganization of NCLL with required professional development. | 1, 2 | Anticipated Outcome 8 | Goals 6, 11 | Laurie Hornbecker | Standard 3 | Staff relocation and reassignment complete with professional development about 85% complete
20 | ADM: CED | Implement Official Transcripts for non-credit students. | 1 | Anticipated Outcomes 1, 9 | Goal 11 | Joan Arbusto Laurie Hornbecker | Standard 6 | Registrar unable to assist with this process. No other resources have been identified at this time. No progress made.
21 | ADM: CED | Produce a trend analysis of non-degree certificates and a plan to promote growth in this area | 1 | Anticipated Outcomes 1, 9 | Goal 11 | Laurie Hornbecker | Standard 6 | A list of programs has been identified but no data collection or analysis is available at this time.
22 | ADM: CED | Reorganize CED program delivery processes to provide staff efficiencies. Produce a trend analysis of non-degree certificates, and a plan to promote growth. | 1, 2, 5 | Anticipated Outcomes 5, 8 | Goals 6, 11 | Laurie Hornbecker | Standard 3 | Instructional support services have been severely reduced. Course entry in Banner, classroom assignment, and invoicing processes have been integrated into remaining clerical staff duties.
23 | ADM: Danbury | Improve efficiency by maximizing the use of classroom space at 183 Main Street, including the 8:40 pm to 10:00 pm time block. Minimize or eliminate use of space at Danbury High School. | Redesign and innovation | FTE enrollment will increase by 20% | full implementation of the proposed plan to expand services in the Danbury area and acquire space in an appropriate location. | Matthew Longcore | Standards 6, 8 | NVCC Danbury Center now utilizes the 8:40 pm to 10:00 pm time block, and has also added Saturday morning courses to the schedule, resulting in more efficient use of space. NVCC courses no longer meet at Danbury High School, resulting in cost savings.
24 | ADM: Danbury | Increase enrollment by adding more credit course offerings at the NVCC Danbury Center, specifically in the areas of General Studies and Liberal Arts. | Redesign and innovation | FTE enrollment will increase by 20% | full implementation of the proposed plan to expand services in the Danbury area and acquire space in an appropriate location. | Matthew Longcore | Standard 6 | Fall 2011 credit enrollment in Danbury set a record at over 800 students. Continued enrollment growth anticipated as Danbury offers a wider selection of credit courses.
25 | ADM: Facilities | Repair roof over Cutrali Commons & Annex with membrane . | 1 | Anticipated Outcomes: 1. FTE enrollment increase. 2. Retention increase. | NA | Robert Divjak | Standard 8 | Complete as of Dec. 9, 2011.
26 | ADM: Facilities | Install photocells on outside lights throughout the college. | 1 | Anticipated Outcomes: 1. FTE enrollment increase. 2. Retention increase. | NA | Robert Divjak | Standard 8 | Master photocell installed on LRC roof. Control work needed to put outside lighting on Johnson Controls BAS.
27 | ADM: Facilities | Replace sodium lights with fluorescent lighting. | 1 | Anticipated Outcomes: 1. FTE enrollment increase. 2. Retention increase. | NA | Robert Divjak | Standard 8 | PO issued to replace HPS lighting with Induction lights. Plan is to do work during winter semester break.
28 | ADM: Facilities | Replace Founders burners on boilers with dual fuel (gas/oil) burners. | 1 | Anticipated Outcomes: 1. FTE enrollment increase. 2. Retention increase. | NA | Robert Divjak Richard Faucher | Standard 8 | Contractor installing one of two new burners. Waiting for another contractor to make the necessary gas meter modifications.
29 | ADM: Facilities | Replace worn out doors and hardware throughout the college. | 1 | Anticipated Outcomes: 1. FTE enrollment increase. 2. Retention increase. | NA | Robert Divjak Leon Luciano | Standard 8 | Doors on order
30 | ADM: Facilities | Replace defective steam controls in FH classrooms for better steam usage. | 1 | Anticipated Outcomes: 1. FTE enrollment increase. 2. Retention increase. | NA | Robert Divjak John Cammuso | Standard 8 | Project started Dec 12, 2011Controlled Air.
31 | ADM: Finance | Implementation of the delivery and accountability for the new bus pass program at NVCC. | 1, 4 | Anticipated Outcome 1 | Goals 5, 9 | Martina Lawlor Lisa Palen | Standard 6 | Process for implementation designed and carried out successfully in Cashiers Office. To date 537 bus passes given out, website updated, flyers made and distributed, NE Transportation bill received and OK'd for payment. Going smoothly.
32 | ADM: Finance | Participate in Bookstore committee to increase bookstore services for both faculty and students. | 1 | Anticipated Outcome 1 | Goals 9, 11 | Lisa Palen | Standard 6 | 1st meeting held Sept. 27th. Well attended. Eight topics were addressed. Next meeting Dec. 6th.
33 | ADM: Finance | Work with individual depts. and divisions in order to achieve better understanding and compliance with procurement regulations. | 1, 4 | Anticipated Outcome 1 | Goal 12 | D. Scott L. Anderson L. Palen | Standard 9 | Worked with the SO, and received clarification on contracting with individuals and their relationship status, and former employees. Implemented and communicated these recommendations. Allied Health and Danbury also received purchasing assistance.• Held meetings with the Student Activities staff to educate them on what needs to come to our office, what types of forms they can and cannot use, and whom to contact with questions. Reviewed the Student Activities Office’s Advisor manual and recommended changes to it.
34 | ADM: IT | Complete IT Strategic Plan. | 1, 3, 4 | N/A | Goal 1 | Conal Larkin and IT SP Cmte | Standards 7, 8 | IT SP being presented to IPC on 12/6/11
35 | ADM: IT | Server consolidation. | 1, 4 | N/A | Goal 1 | Bruce Arsenault Nicholas Schweitzer | Standards 7, 8 | Quote has been revised and ready to submit PO
36 | ADM: IT | Create a staffed tech support bar for students on 5th Avenue similar to an Apple Genius Bar. | 1, 4 | 2, 6 | Goals 1, 4 | Conal Larkin Nephtali Villanueva | Standards 6, 7, 8 | Creating a "GO" cmte to plan and implement
37 | ADM: IT | Network based storage. | 1, 4 | N/A | Goals 1, 4 | Bruce Arsenault Nicholas Schweitzer | Standards 7, 8 | Delayed until blade servers are installed
38 | ADM: WEB | Custom Module Development: Professional Biography and Employee Directory. | 1, 2 | Anticipated Outcomes 1, 6, 7 | Goals 1 | Daniel Wallace | Standard 7 | Underway and scheduled to finish in December.
39 | ADM: WEB | Develop a basic virtual tour featuring areas designed to support student success. | 1, 2 | Anticipated Outcomes 1, 6, 7 | Goals 6, 11 | Daniel Wallace | Standard 7 | Working on Gardens slideshow and ACE tour for Spring 2012
40 | ADM: JPC | Transfer and consolidate staff and resources to implement the Jobs Placement Center. | 1, 2, 5 | Anticipated Outcomes 5, 7, 8, 10 | Goals 6, 11 | Mary Ann Fontaine | N/A | Completed.
41 | ADM: JPC | Explore the feasibility of job placement center robust software to enable 24/7 access to JPC services and expand outreach initiates for employers, students and alumni, as well as data management. | 1, 2, 5 | Anticipated Outcomes 5, 7, 8, 10 | Goals 6, 11 | Mary Ann Fontaine | N/A | Currently in the contract process.
42 | ADM: JPC | Cross-train and do professional development for staff in the JPC to ensure that all have the necessary skills to support students and provide coverage for the JPC. | 1, 2, 5 | Anticipated Outcomes 5, 7, 8,10 | Goals 6, 11 | Mary Ann Fontaine | N/A | Just begun.
43 | ADM: JPC | Determine baseline measures for the JPC and set goals for improvement. | 1, 2, 5 | Anticipated Outcomes 5, 7, 8,10 | Goals 6, 11 | Mary Ann Fontaine | Standard 6 | Multiple measures outlined and presented to the Institutional Effectiveness sub committee of the IPC.
44 | ADM: Public Safety | Reduce/eliminate classroom access issues for credit and non-credit. | 1 | Anticipated Outcomes 2, 3, 4 | Goal 1 | Toni Rinaldi Robert Divjak | Standards 6, 8 | By February will have proposal as prepared by Lt. Rinaldi and Facilities Dir. Divjak
45 | ADM: Public Safety | Create and install emergency information signs for each work/study space on campus. | 1 | Anticipated Outcomes 2, 3, 4 | Goal 1 | Toni Rinaldi Tom Violante | Standard 6 | Graphic designer not currently available to work on this project; will explore alternate options.
46 | HR | Develop procedure for electronic submission of application for part time adjunct positions. | 1 | NA | Goal 1 | Jacqueline Swanson | Standards 3, 7, 9 | Completed. Awaiting response on technical areas from IT in order to fully implement.
47 | HR | Continuous improvement of the HR pages and links on the College web site. | 1 | NA | Goal 1 | Jacqueline Swanson | Standards 3, 7, 10 | Ready to implement. Will attend assistance program scheduled for 12/9/11 once it is announced.
48 | HR | Encourage employees to sign up for direct deposit. | 1 | NA | Goal 1 | Yolanda Crowder Kathleen Nicholson | Standards 3, 9 | On-going
49 | HR | Advocate organizational structures that effectively manage resources and deliver services. | 1 | NA | Goal 1 | A. J. DuBois Jacqueline Swanson | Standard 3 | On-going. Events Management, Job Placement Center, CAPSS, Institutional Advancement.
50 | HR | Recruit and train new staff for Payroll and Human Resources. | 1 | NA | Goal 1 | A. J. DuBois Jacqueline Swanson | Standard 3 | HR person in place and in training/payroll person half time and in training

## WIG 3
WIG 3. Diversify and strengthen resource development and external funding.
| Unit: Department | Initiatives and Activities | WIGs Lever | "10 Anticipated Outcomes" | Presidential Goal | Leader(s) for Implementation | NEASC Standard | Status: Dec. 1 | Status: Mar. 1 | Final Status: May 1
1 | AA | Strengthen grants management, especially in the newly created STEM Division; encourage faculty to attend sessions on reading and writing grants | Redesign and innovation; Professional development | Anticipated Outcome 6 | Goals 3, 15 | Sandra Palmer Estela Lopez | Standard 4 | Applications for two STEM-related grants have gone out, one in conjunctions with UCONN, the other through the SO.
2 | ADM: Dean | Coordinate an effort on campus to work with an engineering firm selected by DPW to design the campus-wide improvement project. | 1 | 6 | Anticipated Outcome 6 | James Troup Robert Divjak | Standard 8 | Participated in a selection process in which engineering firm was selected by DCS. As soon as contract is signed by DCS, planning process will begin--with college participation.
3 | ADM: Dean | Coordinate an effort on campus to assist in the selection of and engineering firm for the design of the Founders Hall/Center for Allied Health Project; begin coordination of college participation in the planning and design of this project. | 1 | 6 | Anticipated Outcome 6 | James Troup Robert Divjak | Standard 8 | Advertisement was placed on 11/24/11 by DCS for architect. Interview/selection process may occur in Feb. 2012, with college participation
4 | ADM: CED | Manage current grant awards to successful completion. | 1, 4, 6 | Anticipated Outcomes 6, 8 | Goal 11 | Laurie Hornbecker | Standard 9 | Grants identified and assigned to new staff members. A management learning curve is underway. Monitoring reports have been submitted with assistance from Angela Moffat.
5 | ADM: CED | Explore the potential to partner with the NRWIB on further green training initiatives through their grant. | 1 | Anticipated Outcome 4 | Goal 11 | Laurie Hornbecker Lisa Crick | Standard 9 | Periodic meetings with representatives of the WIB continue to be stalled over the lack of employment in these fields. Discussions may take place in a few months
6 | ADM: CED | Develop a marketing plan with strategies to promote the changing non-credit program mix | 1, 4, 6 | Anticipated Outcomes 5, 8 | Goal 11 | Jim Troup Laurie Hornbecker | Standard 9 | No progress has been made. This initiative is temporarily deferred until the marketing department is stabilized and appropriate resources are available to develop a plan, perhaps by spring 2012.
7 | ADM: Danbury | Work with the NVCC Foundation and City Center Danbury to host a fundraising event at the Danbury Center. Raise money for scholarships dedicated to Danbury area students. | Integration of academic and student success | Retention rate will increase by 20% | full implementation of the proposed plan to expand services in the Danbury area and acquire space in an appropriate location. | Matthew Longcore Waldemar Kostrzewa | Standard 9 | Matt Longcore attended the Latino Scholarship Dinner in Danbury and believes it to be a good model of what could be achieved for the NVCC Danbury Center. Matt Longcore will meet with Wally Kostrzewa to discuss this idea.
8 | ADM: Finance | Grant accounting to continue to be more refined and responsive to the needs of NVCC grant recipients and granting authorities. | 4 | Anticipated Outcome 6 | Goal 15 | Angela Moffat Lisa Palen | Standard 9 | Processing more than 14 grants. Met with grant coordinators to set up banner budgets and review expenditures to meet monthly and quarterly reporting deadlines, refined accountability to be more descriptive on grant expenditures. Proactive approach to implementing grant accounting processes at MOU timeframe, working with SO to get more efficient in getting payroll charged to grants.
9 | ADM: IT | Document policies and procedures. | 4 | N/A | Goal 1 | Conal Larkin Nephtali Villanueva | Standards 3, 7,8 | 10 procedures a new IT employee should know being created.
10 | ADM: IT | Create a service catalog. | 4 | N/A | Goal 1 | Conal Larkin Nephtali Villanueva | Standards 7, 8 | Services offered being documented.
11 | ADM: Web | Google Analytics: track, measure and report web traffic via general and custom reports to departments and divisions. | 1, 3, 4 | N/A | Goals 8, 12 | Daniel Wallace | Standard 10 | Waiting until academic and navigation redesign completed.
12 | ADM: Web | Prepare and adopt a strategic plan for Web Services. | 3, 4 | N/A | Goals 13, 14 | Daniel Wallace | Standard 10 | Assembling committee to work on plan.
13 | ADM: Public Safety | Explore grant-funded opportunities to support departmental needs and campus initiatives related to public safety. | 3 | Anticipated Outcome 6 | Goals 15 | Toni Rinaldi Waldemar Kostrzewa | Standard 9 | Investigated partnering on grant with TXCC for emergency preparedness. Grant availability to be announced in spring 2012.
14 | OCE | Assist in NVCC Foundation Board Development. | 1 | Anticipated Outcome 6 | Goal 15 | Foundation members, Dean of OCE,and NVCC President. | Standards 9, 12 | Foundation has appointed board development chair. Board and NVCC materials prepared for new-member prospecting. All directors asked to nominate. New member expected in December.
15 | OCE | Reinvigorate the NVCC Alumni Association. | 1 | Anticipated Outcome 6 | Goal 13 | OCE Dean, NVCC Foundation board, and NVCC President. | Standards 9, 12 | Leadership names being submitted. Effort to be re-started after upcoming holidays.
16 | OCE | Establish a Grants Planning and Management System. | 1 | Anticipated Outcome 6 | Goal 15 | NVCC Cabinet, and OCE. | Standards 9, 12 | Planning and management materials being updated for Cabinet approval and college distribution in February.
17 | OCE | Establish a Facilities Naming Advisory Committee. | 1 | Anticipated Outcome 6 | Goal 15 | Dean of OCE and NVCC President. | Standards 9, 12 | Meeting to be set with Cabinet for final review of committee nominees. Committee chair has been recommended. Review of campus naming opportunities will be drafted in February.